## Instructions
Local Government Energy Efficiency Strategic Plan Menu (SPM) - Bi-Annual Reporting
Questions? Contact your IOU Program Manager
IOU Partner:
SCE
Reporting Period:
| Start: | 2016-07-01
| End: | 2016-12-31
Submission Deadline: |  | 2016-10-28
General Instructions
Please complete the "SPM Report" tab for new strategic plan menu (SPM) items from 2016 and continuing SPM items not reported as "Complete" in the 2013-15 cycle.
Please omit any activity completed prior to January 1, 2016.
You will find a complete list of SPM items in the tab labeled "SPM_MenuItems" as reference.
New Projects: | Projects initiated after January 1, 2016.
For each new project, complete all cells within a blank row immediately below the last populated row. Upon review with your Program Manager, the cells highlighted gray will be locked from future editing. This is to facilitate understanding of project scope, and to encourage dialogue regarding changes to scope.
Continuing Projects: | Projects initiated before the current reporting period, which are ongoing.
For continuing projects, changes in initial project scope should be specified. - Revisions to Project Timeline: Changes to the project's timeline should be noted in Column X. - Revisions to Budget: If the budget for a project changes, the new cumulative budget should be reported in Column Y. - Changes to Project Scope: Changes to the project scope (goal, local governments served, etc.) should be noted in Column Z. - Additional details regarding changes in project scope can be detailed in the Narrative Report section.
Completed Projects: | Projects completed after January 1, 2016.
Select "Completed" from the drop-down menu in Column U.
Specify the accomplishments of the project in Column V, and note "Final" in the text. If scoped deliverables are not completed, specify which in Column T.
If a project was completed before or after the planned timeline, specify the completion date in Column X, and note "Final" in the text.
If a project was completed above or below the planned budget, specify the final expenditures in Column Y, and note "Final" in the text.
Cancelled Projects: | Projects which were initiated, but which are deemed to proceed no further.
To the extent possible, document all relevant information in the corresponding cells (e.g. expenditure, accomplishments, etc.).
Provide narrative summary of the actions or inactions that led to the project being cancelled.
If learned lessons can be gleaned from cancelled projects, specify in Column AM (Lessons Learned).
Projects On-Hold: | Projects which are still planned to occur, but which face unanticipated delays.
Provide narrative summary of the actions or inactions that led to the project being placed on-hold. Specify what actions (if known) need to be addressed before the project can resume.
Instructions by Section
Project Scope | Each project line item should be mutually exclusive, and should not include the accomplishments of another.
If project relates to a past project, indicate how it relates using the drop-down in Column E. Specify which past project in the Description in Column F. - New Project: Current project does not directly relate to past project - New Phase of Past Project: Past project as scoped and completed previously; current project builds upon the accomplishments of the past project. - Re-Launch of Past Project: Past project was scoped and either completed, placed on-hold, or cancelled; current project attempts the same/similar effort as past project, but with new project elements to address lessons learned. - Update of Past Project: Past project was scoped and completed previously; current project integrates new information, as in updates to previously adopted code or Climate Action Plan.
Report all project information based on its current, cumulative scope. For instance, provide the full, anticipated cumulative budget based on the scoped goal and timeline.
Select all sectors applicable to the work being performed.
Projects should have a clear beginning and end date.
Projects should have a defined budget. Please report cumulative budget corresponding to the defined timeline.
SPM Alignment | Projects should be scoped to address one primary SMP Item. In some cases, projects may support additional SMP Items; however, if projects are broad enough to cover multiple SMP Items, they should be separately scoped and reported.
Progress Indicators | Specify the deliverables and/or metrics that will mark progress toward completing the goal. For a list of recommended metrics corresponding to SPM goals, refer to the "SPM Menu Items" tab, Column E.
Specify the primary goal of the project. The goal should correspond to the SPM Item the project supports.
If a code-related project, specify whether the goal is to adopt code(s), or to provide other code-support; if the goal is to adopt code(s), specify whether the code(s) are voluntary or mandatory.
To the extent possible, quantify the number of policy documents/plans, anticipated kWh savings and public workshops (as applicable).
Project Status and Accomplish-ments to Date | All projects should have a defined project status (e.g. In Progress, On-Hold, Complete, Cancelled). The project timeline (Start Date / Completion Date) should correspond with project status. If the timeline and status are out of alignment, the cells will highlight red to identify the discrepency.
Accomplishments to-date should refer to deliverables and/or metrics. Report unanticipated or spill-over benefits in the Narrative Report section, and Lessons Learned section (if applicable).
If deliverables or metrics are tied to local governments as recipients (e.g. each city receives a benchmarking report), provide status updates specific to each local government.
Local Government Officials Engaged* | In Columns AA-AE, track the number of government officials or public stakeholers of various types engaged during the reporting period (e.g. January - June).
In Column AF, track the cumulative number of government officials/public stakeholders engaged throughout the duration of the project. This value should draw upon values previously reported.
Narrative Reporting | Provide detailed account of progress made to date, significant acheivements, significant challenges, deliverables or milestones completed, lessons learned, and knowledge transferred. Include anything in this section that could not be clearly articulated in other appropriate cells.
Knowledge Transfer | Document major findings emerging from project implementation under the Lessons Learned section. This should be cumulative, covering the full project duration
If work product is published online, please provide links to the material.

## SPM_Report
Review the grey cells below to ensure the information on your projects remains correct in this reporting period. Scroll to the right to share project updates in all white cells. Contact your IOU Project Manager with any questions.
|  | Project ID |  | Project Scope | [8 empty] | SPM Alignment |  | Progress Indicators |  |  |  |  | Project Status and Accomplishments to Date | [5 empty] | Engagements (This Reporting Period) | [5 empty] | Narrative Reporting | Narrative Reporting | Narrative Reporting | Narrative Reporting | Narrative Reporting | Narrative Reporting | Knowledge Transfer
Due Date |  | Partnership Name | Project Name | Connection to Past Project? | Project Scope and Description (Max 600 Characters) | Applicable Sector | Primary Beneficiary/ies | Multi-IOU Project? | Start Date (MONTH-YYYY) | Original Estimated Completion Date (MONTH-YYYY) | SCE Budget Allocation to Project | Matching Funds Amount and Detail (if applicable) | Primary SPM Item Alignment | Secondary SPM Item Alignment (if applicable) | Specify Deliverable and/or Evaluative Metric | Goal | # Plans or Policies to be Developed (optional) | Estimated Electricity Savings (kWh) (optional) | # of Outreach Events to be Held (optional) | Project Status | Scope Completed to Date | Scope Remaining to be Completed | Revisions to Project Timeline? | Revisions to Project Budget? | Revisions to Project Scope? | Elected / Appointed Officials | Dept Directors / City Manager | Other local gov't staff | Support Staff / Consultant / IOU / Non-Govt | Public / Community Members | Total Engagements | October 2016 Narrative Update (January 1 - June 30, 2016) | March 2017 Narrative Update (July 1 - December 31, 2016) | September 2017 Narrative Update (January 1 - June 30, 2017) | March 2018 Narrative Update (July 1 - December 31, 2017) | September 2018 Narrative Update (January 1 - June 30, 2018) | March 2019 Narrative Update (July 1 - December 31, 2018) | Lessons Learned Reporting (Cumulative) | Links to Work Product or Deliverable?
2016-12-31 | 1899-12-31 | San Gabriel Valley Energy Leader Partnership | Develop and Adopt a Voluntary Green Building Program | 2013-2015 Continuation | Phase 3: 2. San Gabriel Valley Council of Governments will develop a voluntary green building program (San Gabriel Valley Green Building Initiative) that increases the installation of EE equipment for existing construction through education and outreach. Implementer will: - Develop a Green Building Guidebook with regionally relevant content for residents, builders and developers; - Review Energy Action Plans for Participating Municipalities (PMs) for EE strategies for the Green Building Guidebook; - Develop the Green Building Regional website and customize pages for PMs that contain city-specific energy information, programs, and goals. | Public Residential Commercial | Cities of Alhambra, Arcadia, Baldwin Park, Bradbury, Claremont, Covina, Diamond Bar, Duarte, El Monte, Irwindale, La Canada Flintridge, Monterey Park, Pomona, Rosemead, San Dimas, San Gabriel, South El Monte, South Pasadena, Temple City, Walnut, West Covina | N/A | 2013-08-01 | 2015-07-01 | 84100 | 0 | 1.1.2. Green Building Code | N/A | 1. Green Building Regional Portal Website Content 2. Final Green Building Guidebook 3. Live and Fully Functional Green Building Regional Portal Website | The goal of this task to develop the San Gabriel Valley Green Building Initiative to drive building performance that exceeds Title 24 requirements by capitalizing on the unique position and role that local government has in reviewing construction activity taking place in the city. | 0 |  |  | Complete | 1.Final Green Building website content approved. Website active and continues to be updated. 2. Submitted Final Green Building Guidebook to stakeholders. Final report will be submitted shortly. 3. Educational home improvement handouts are complete and are currently being distributed to all the cities in the SGV. 4. Final best practices report submitted. | 1. Final program reports submitted in July 2016. | To be completed September 2016. | None | None | 0 | 48 | 120 | 0 | 1000 | 1168 | 1.Final Green Building website content approved. Website active and continues to be updated. 2. Submitted Final Green Building Guidebook to stakeholders. Final report will be submitted shortly. 3. Educational home improvement handouts are complete and are currently being distributed to all the cities in the SGV. 4. Final best practices report submitted. | Submitted final report in July 2016. |  |  |  |  | Early Engagement of Homeowners: The original program design focused on engaging homeowners when they were seeking permits, with the goal of informing them of potential modifications they could make to their planned projects to increase the energy efficiency of their home. However, after discussions with city staff and other stakeholders and further research of other programs, staff determined that it is critical to engage homeowners prior to the start of any major renovation project. This accomplishes several goals: 1) influencing the products, materials and installation method a homeowner might select on a project that they have already committed to undertaking; 2) influencing homeowners to undertake a new project that they may not have been considering; and 3) educating homeowners about the importance of securing a building permit for applicable projects in order to ensure proper installation and performance. By the time a homeowner is seeking a permit, they have usually solidified a scope of work, set a budget, and selected a contractor. Therefore, it is very difficult to influence that project. | http://www.sgvenergywise.org/green-building-guidebook
2016-12-31 | 1899-12-31 | San Gabriel Valley Energy Leader Partnership | Redesign Enforcement, Compliance, Plan Review Processes | 2013-2015 Continuation | Phase 3: San Gabriel Valley Council of Governments will redesign the inspection process by developing an EE Point-of-Permit Program. Materials include forms, templates, checklists, and marketing materials, and training to integrate EE elements into city permit and inspection processes. Each participating municipality (PM) can choose from two options: • Level One includes using checklists during the pre-inspection process. • Level Two includes a mandatory assessment, and will require the PM to conduct an assessment for major renovations. | Public Residential Commercial | Cities of Alhambra, Arcadia, Bradbury, Claremont, Covina, Diamond Bar, El Monte, Irwindale, La Canada Flintridge, Monterey Park, Pomona, Rosemead, San Dimas, South El Monte, South Pasadena, Temple City, West Covina | N/A | 2013-08-01 | 2015-06-01 | 202300 | 0 | 2.1.2. Code Compliance and Enforcement | N/A | 1. Final Procedures for Implementing Program for Each Participating Municipality 2. Energy Efficiency Checklist 3. Report on Training City Staff to Implement Program 4. Report on Program Launch | The goal of this task is to incorporate EE into the inspection process, and modify the role of building and safety departments to increase the installation of EE for Participating Municipalities.. | 0 |  |  | Complete | 1. Held staff training on checklist in December 2014. 2. Submitted draft implementation procedures to SCE in December 2014. 3. Held staff trainings on home assessment procedures in participating cities in January 2015. 4. Launched program in participating cities and delivered educational materials in January and February 2015. 5. Staff conducting home assessments and collecting implementation data from participating residents. 6. Final report on Program Launch has been submitted. 7. Final best practices report has been submitted. | 1. Final program reports submitted in August 2016. | To be completed by August 2016. | None | None | 0 | 24 | 60 | 0 | 711 | 795 | 1. Submitted final program report. 2. Submitted final best practices report. | Submitted final report in August 2016 |  |  |  |  | Some of the key lessons learned from the project include engaging homeowners before they have begun planning projects or seeking permits; developing an extensive education and outreach plan; and providing comprehensive information about related programs and financing offerings that can assist with implementation of projects. | http://www.sgvenergywise.org/easy
2016-12-31 | 1899-12-31 | South Santa Barbara County Energy Leader Partnership | Energy Efficiency Standard for County Owned Facilities | 2013-2015 Continuation | Phase 3: The County of Santa Barbara will develop an EE standard for county facilities to increase the level of EE in those buildings and facilities. The standard will be structured as a resolution, which will make it mandatory for qualified construction projects. In addition to the standard an implementation guide will be developed to assist staff in working with the EE standard. The standard and associated documents will be submitted to the Board of Supervisor for approval. | Public | County of Santa Barbara | N/A | 2013-08-01 | 2015-09-01 | 84616 | 0 | 1.1.2. Green Building Code | N/A | 1. Final EE Standard for County Owned Facilities and Implementation Guide approved by Board of Supervisors | The goal of this task is to develop and implement a mandatory EE standard for county facilities that is more stringent than current applicable codes. | 1 |  |  | Complete | 1. Draft EE Standard completed 2. Staff report being finalized 2. Draft policy completed | 1. Board of Supervisors Approval 2. Training of County Staff | To be completed by August 2016. | None | None | 0 | 0 | 0 | 0 | 0 | 0 | 1. Staff report was finalized and on County board agenda for the month of August 2016 | 1. As of Aug. 20th, the Board unanimously approved the EE Standard 2. Staff Training is being coordinated through SCE's Codes and Standards group to allow for an ongoing level of support for County Staff |  |  |  |  | The approval process for local government policies is long and it must be recognized that energy-related policies require significant education to influence stakeholders and policy makers. Stakeholders such as facilities staff and project managers must be made aware of and understand their responsibility for implementing sections relevant to their project role. Stakeholders are many, spread across several departments and therefore regular communication and training will be necessary to ensure compliance with the Standard. Ongoing training is critical to ensure compliance. The County will look to its utility partners for training support throughout the year to reinforce key aspects of the Standard such as compliance with Title 24, CalGreen and better understanding of Zero Net Energy buildings. | https://santabarbara.legistar.com/LegislationDetail.aspx?ID=2819679&GUID=B45B593E-FFA8-4894-A68A-E1BDC65583C8
2016-12-31 | 1899-12-31 | Western Riverside Energy Leader Partnership | On-Line Permitting | 2013-2015 Continuation | Phase 3: Western Riverside Council of Governments will purchase and install on-line permitting systems for the cities of Perris and Wildomar. Perris will install and implement a complete on-line permitting system, utilizing the approach taken by other member cities of WRCOG during Phase 2 of the SP Program. The software proposed will be compatible with the Perris’ financial system. Wildomar will enhance its existing online permitting system (installed during the Phase 1 of the SP Program) by adding a code enforcement module to further integrate online permitting system into permitting operations. | Public Residential Commercial | Cities of Perris and Wildomar | N/A | 2013-08-01 | 2015-04-01 | 87000 | 0 | 1.1.5. Energy Efficiency Codes & Programs | N/A | The new online system will collect data on energy-efficient building projects, and this data will be made available through WRCOG and the Western Riverside Energy Leaders Partnership websites, quarterly electronic newsletters, and quarterly Partnership meetings. | The goal of this task is to install on-line permitting systems at the two Participating Municipalities which are expected to increase code compliance and installation of EE measures among city constituents and developers. | 1 |  |  | Complete | 1. The on-line permitting system for the City of Perris is installed and operational. The City is promoting the use of the system. 2. The City of Wildomar's on-line permitting system has been enhanced to include a code enforcement module. It has been installed and implemented. 3. Policies and procedure drafted, reviewed, and completed for the City of Perris and Wildomar 4. Compilation of Training materials and training report developed for Utility review 5. Develop Best Practices / Lessons learned report | 1. Final Report | To be completed by Nov 2016 (Completed December 2016) | None | None | 0 | 2 | 19 | 0 | 0 | 21 | 1. The City of Perris is up and running with its new Online Permitting system. On each permit, online information is provided on how future permits can be completed online. 2. The City of Wildomar has provided online permitting services to its residents for a few years, funded by the Phase 2 SP solicitation funding, but per this funding the City enhanced the current Online Permitting system to add code enforcement functions to ensure a higher level of quality control on the energy efficiency projects. | WRCOG Staff has completed and provided final Strategic Plan report along with supplemental materials pertaining to both the Cities of Perris and Wildomar's Online Permitting System. The documents were turned into SCE on December 2016. City of Wildomar Staff is still creating educationla videos to provide to their users of the online permitting system. Both the Cities of Perris and Wildomar's Online Permitting System continue to provide valuable information and assist with the cities day to day work environment. |  |  |  |  | • City of Perris: The installation of the on-line permitting system has helped the City of Perris provide additional information to applicants that are interested in any rebate incentives that are available for application. • City of Wildomar: One of the biggest lessons learned from implementing this system was that it provided a learning growth rate of how to use the module. • Both organizations involved in the development and implementation of the Online Permitting System learned that education of the system for both staff and residents was heavily important to obtain results and feedback on the system. | Perris: https://aca.accela.com/perris/default.aspx Wildomar: https://permits.cityofwildomar.org/Default.asp?Build=PM.pmPermit.Apply1&Mode=ClearBo&BOName=pmPermit
2016-12-31 | 1899-12-31 | Western Riverside Energy Leader Partnership | Revolving Energy Efficiency Fund | 2013-2015 Continuation | Phase 3: Western Riverside Council of Governments will develop a Regional Revolving Energy Efficiency Fund (RREEF) will be established for participating cities. This task will include the following activities: • Identify seed funding for RREEF • Develop a RREEF administrative manual with operating procedures and worksheet models to assist administrators with fund management • Establish the fund, including the development of staff approval materials, presentations to necessary board committees, and coordination with auditors and counsel (internal and external) to properly establish a distinct fund for this purpose. | Public | Cities of Calimesa, Canyon Lake, Eastvale, Hemet, Lake Elsinore, Menifee, Murrieta, Norco, Perris, San Jacinto, Temecula, and Wildomar | N/A | 2013-08-01 | 2015-06-01 | 126150 | 0 | 3.2.3. Local Gov't Revolving Energy Efficiency Fund | N/A | 1. Report on Identification of Seed Funding for RREEF 2. Administrative Manual | The goal of this task is to establish a Regional Revolving Energy Efficiency Fund to provide a sustainable source of funding for EE projects for Participating Municipalities. | 1 |  |  | Complete | 1. Draft RREEF documents prepared for review: RREEF Administrative Manual, Operations Checklist, and Master Purchase lease documents 2. Final RREEF documents: RREEF Administrative Manual, Operations Checklist, Master Purchase lease documents 3. Identifies potential list of energy efficiency projects at municipal facilities | 1. Final Report | To be completed by Nov 2016 (Completed December 2016) | None | None | 0 | 0 | 0 | 0 | 0 | 0 | 1. Completing final deliverables and final report 2. WRCOG will continue to identify energy efficiency projects and promote the Revolving Loan fund as an option for energy efficiency project financing | WRCOG Staff has completed and provided final Strategic Plan report along with supplemental materials pertaining to WRCOG's implementation of a Revolving Energy Efficiency Fund (REEF) The documents were turned into SCE on December 2016. |  |  |  |  | • One of the biggest challenges about the Revolving Fund was identifying how to start Program. • Cities that are interested in using the funds from this Program will be limited to a certain amount so other interested cities may tap into this fund if they have any EE/Water/Sustainability projects in mind. | N/A
| 2016-12-31 | San Joaquin Energy Leader Partnership (AKA VIEW Partnership) | Benchmarking in Energy Star Portfolio Manager | New Phase of Past Project (specify in Description) | Embedded 2013-2015: San Joaquin Valley Clean Energy Organization will benchmark of all utility accounts in Energy Star Portfolio Manager (ESPM) for VIEW partners. Also includes training of local government staff on use of Portfolio Manager. | Public | Cities of Porterville, Tulare and Woodlake and Counties of Kings and Tulare | PG&E / SCE / SCG | 2015-01-01 | 2016-12-01 | $13,500 (PG&E) / $13,500 (SCE) / $1,400 (SCG) | 0 | 3.1.1. Local Gov't Benchmarking Policies | N/A | Benchmarked portfolios for the County of Tulare and the Cities of Avenal, Corcoran, Dinuba, Hanford, Lemoore, Porterville, and Tulare. All utility accounts will be benchmarked in ESPM, City will use a benchmarking policy to impact procurement and investment decisions, and staff will be trained on program use. | Municipal staff in all local governments enrolled in Portfolio Manager and automated benchmarking services and actively engaged in data analysis. | 5 | 16441200 | 0 | In Progress | 1. Completed benchmarking for: County of Kings, Cities of Avenal, Dinuba, Hanford, Woodlake | 1. Complete SCG benchmarking for Tulare County and Cities of Porterville and Tulare. Begin benchmarking processes for Corcoran and Lemoore | Project to continue in 2017 for Tulare County. Project has not been started for Corcoran or Lemoore. | None | None | 1 | 0 | 4 | 2 | 0 | 7 | 1. City and county energy accounts have been scrubbed for accuracy and duplicates/dead accounts have been removed from the portfolio 2. Met with city/county staff to review facility characteristics 3. Worked with IOU representatives to collect accurate energy data and set up Automatic Benchmarking for the cities and counties. 4. Benchmarking is now complete for the County of Kings as well as the Cities of Avenal, Dinuba, Farmersville, Hanford, Lindsay, Visalia, and Woodlake. | 1. No changes. Continue to perform maintenance as necessary. 2. Working with County of Tulare to get accurate building data characteristics for one-time data upload into ESPM. |  |  |  |  | 1. ESPM glitches include a) duplicated SCE data, requiring account review and maintenance when data reports are needed and b) no SCG energy usage cost uploads, prohibiting local government staff and implementer staff to fully report on and analyze usage data. 2. Local governments that lack comprehensive facility inventories add significant workload to the benchmarking process. | TBD
| 2016-12-31 | San Joaquin Energy Leader Partnership (AKA VIEW Partnership) | Energy Action Plans | New Phase of Past Project (specify in Description) | Embedded 2013-2015: San Joaquin Valley Clean Energy Organization will create customized Energy Action Plans or Climate Action Plans to fit the needs of individual cities while maintaining a regional focus. | Public Residential Commercial Industrial Agricultural | City of Hanford and County of Kings | PG&E / SCE / SCG | 2015-01-01 | 2016-12-01 | $13,500 (PG&E) / $13,500 (SCE) / $1,400 (SCG) | 0 | 4.1.2. Customized EAP/CAP | N/A | Council ready EAP. The EAP may or may not be approved by council (concerns regarding document as a planning document exist and are being reviewed by local government counsel). If document is not formally adopted the LG will institute department strategies and use the document as a guiding principle document to influence staff activities. | Adoption, either at council or internally, of a customized energy action plan. | 2 | 0 | 0 | In Progress | 1. Kings County EAP complete and approved 2. City of Hanford EAP complete; on hold until Spring 2017 | 1. Begin EAP process for all other VIEW jurisdictions. | Project to continue into 2017 as EAPs for other VIEW jurisdictions are started. | None | None | 0 | 1 | 5 | 3 | 0 | 9 | 1. The County of Kings has completed the development of its EAP and, once the County completes document review, will bring the document to Council for approval 2. The City of Hanford has adopted a CAP independent of the Partnership. The City has completed approximately 70% of its EAP. | 1. The County board and SCE approved the Energy Action Plan for the County of Kings. This allowed the County to move to Gold on the SCE tier ladder and begin preparations for implementation of the Plan. 2. The EAP for the City of Hanford was completed and presented to the City. Due to an upcoming update to the City's General Plan and the election of new Council members, the City has put a hold on moving forward with the EAP until Spring 2017. |  |  |  |  | Each local government requires different language and layouts of EAPs, which can sometimes significantly increase the workload of this project. | TBD
| 2016-12-31 | [29 empty] | 0
| 2016-12-31 | [29 empty] | 0
| 2016-12-31 | [29 empty] | 0
| 2016-12-31 | [29 empty] | 0
| 2016-12-31 | [29 empty] | 0
| 2016-12-31 | [29 empty] | 0
| 2016-12-31 | [29 empty] | 0
| 2016-12-31 | [29 empty] | 0
| 2016-12-31 | [29 empty] | 0
| 2016-12-31 | [29 empty] | 0
| 2016-12-31 | [29 empty] | 0
| 2016-12-31 | [29 empty] | 0
| 2016-12-31 | [29 empty] | 0
| 2016-12-31 | [29 empty] | 0
| 2016-12-31 | [29 empty] | 0
| 2016-12-31 | [29 empty] | 0
| 2016-12-31 | [29 empty] | 0
| 2016-12-31 | [29 empty] | 0
| 2016-12-31 | [29 empty] | 0
| 2016-12-31 | [29 empty] | 0
| 2016-12-31 | [29 empty] | 0
| 2016-12-31 | [29 empty] | 0
| 2016-12-31 | [29 empty] | 0
| 2016-12-31 | [29 empty] | 0
| 2016-12-31 | [29 empty] | 0
| 2016-12-31 | [29 empty] | 0
| 2016-12-31 | [29 empty] | 0
| 2016-12-31 | [29 empty] | 0
| 2016-12-31 | [29 empty] | 0
| 2016-12-31 | [29 empty] | 0
| 2016-12-31 | [29 empty] | 0
| 2016-12-31 | [29 empty] | 0
| 2016-12-31 | [29 empty] | 0
| 2016-12-31 | [29 empty] | 0
| 2016-12-31 | [29 empty] | 0
| 2016-12-31 | [29 empty] | 0
| 2016-12-31 | [29 empty] | 0
| 2016-12-31 | [29 empty] | 0
| 2016-12-31 | [29 empty] | 0
| 2016-12-31 | [29 empty] | 0
| 2016-12-31 | [29 empty] | 0
| 2016-12-31 | [29 empty] | 0
| 2016-12-31 | [29 empty] | 0
| 2016-12-31 | [29 empty] | 0
| 2016-12-31 | [29 empty] | 0
| 2016-12-31 | [29 empty] | 0
| 2016-12-31 | [29 empty] | 0
| 2016-12-31 | [29 empty] | 0
| 2016-12-31 | [29 empty] | 0
| 2016-12-31 | [29 empty] | 0
| 2016-12-31 | [29 empty] | 0
| 2016-12-31 | [29 empty] | 0
| 2016-12-31 | [29 empty] | 0
| 2016-12-31 | [29 empty] | 0
| 2016-12-31 | [29 empty] | 0
| 2016-12-31 | [29 empty] | 0
| 2016-12-31 | [29 empty] | 0
| 2016-12-31 | [29 empty] | 0
| 2016-12-31 | [29 empty] | 0
| 2016-12-31 | [29 empty] | 0
| 2016-12-31 | [29 empty] | 0
| 2016-12-31 | [29 empty] | 0
| 2016-12-31 | [29 empty] | 0
| 2016-12-31 | [29 empty] | 0
| 2016-12-31 | [29 empty] | 0
| 2016-12-31 | [29 empty] | 0
| 2016-12-31 | [29 empty] | 0
| 2016-12-31 | [29 empty] | 0
| 2016-12-31 | [29 empty] | 0
| 2016-12-31 | [29 empty] | 0
| 2016-12-31 | [29 empty] | 0
| 2016-12-31 | [29 empty] | 0
| 2016-12-31 | [29 empty] | 0
| 2016-12-31 | [29 empty] | 0
| 2016-12-31 | [29 empty] | 0
| 2016-12-31 | [29 empty] | 0
| 2016-12-31 | [29 empty] | 0
| 2016-12-31 | [29 empty] | 0
| 2016-12-31 | [29 empty] | 0
| 2016-12-31 | [29 empty] | 0
| 2016-12-31 | [29 empty] | 0
| 2016-12-31 | [29 empty] | 0
| 2016-12-31 | [29 empty] | 0
| 2016-12-31 | [29 empty] | 0
| 2016-12-31 | [29 empty] | 0
| 2016-12-31 | [29 empty] | 0
| 2016-12-31 | [29 empty] | 0
| 2016-12-31 | [29 empty] | 0
| 2016-12-31 | [29 empty] | 0
| 2016-12-31 | [29 empty] | 0
| 2016-12-31 | [29 empty] | 0
| 2016-12-31 | [29 empty] | 0
| 2016-12-31 | [29 empty] | 0
| 2016-12-31 | [29 empty] | 0
| 2016-12-31 | [29 empty] | 0
| 2016-12-31 | [29 empty] | 0
| 2016-12-31 | [29 empty] | 0
| 2016-12-31 | [29 empty] | 0
| 2016-12-31 | [29 empty] | 0
| 2016-12-31 | [29 empty] | 0
| 2016-12-31 | [29 empty] | 0
| 2016-12-31 | [29 empty] | 0
| 2016-12-31 | [29 empty] | 0
| 2016-12-31 | [29 empty] | 0
| 2016-12-31 | [29 empty] | 0
| 2016-12-31 | [29 empty] | 0
| 2016-12-31 | [29 empty] | 0
| 2016-12-31 | [29 empty] | 0
| 2016-12-31 | [29 empty] | 0
| 2016-12-31 | [29 empty] | 0
| 2016-12-31 | [29 empty] | 0
| 2016-12-31 | [29 empty] | 0
| 2016-12-31 | [29 empty] | 0
| 2016-12-31 | [29 empty] | 0
| 2016-12-31 | [29 empty] | 0
| 2016-12-31 | [29 empty] | 0
| 2016-12-31 | [29 empty] | 0
| 2016-12-31 | [29 empty] | 0
| 2016-12-31 | [29 empty] | 0
| 2016-12-31 | [29 empty] | 0
| 2016-12-31 | [29 empty] | 0
| 2016-12-31 | [29 empty] | 0
| 2016-12-31 | [29 empty] | 0
| 2016-12-31 | [29 empty] | 0
| 2016-12-31 | [29 empty] | 0
| 2016-12-31 | [29 empty] | 0
| 2016-12-31 | [29 empty] | 0
| 2016-12-31 | [29 empty] | 0
| 2016-12-31 | [29 empty] | 0
| 2016-12-31 | [29 empty] | 0
| 2016-12-31 | [29 empty] | 0
| 2016-12-31 | [29 empty] | 0
| 2016-12-31 | [29 empty] | 0
| 2016-12-31 | [29 empty] | 0
| 2016-12-31 | [29 empty] | 0
| 2016-12-31 | [29 empty] | 0
| 2016-12-31 | [29 empty] | 0
| 2016-12-31 | [29 empty] | 0
| 2016-12-31 | [29 empty] | 0
| 2016-12-31 | [29 empty] | 0
| 2016-12-31 | [29 empty] | 0
x | x | x | xx | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | [5 empty] | x | x

## SPM_MenuItems
Goal | Strategy | Menu Option - Abbreviated Title | Menu Option- Full Text | Metric
1 - Local governments lead adoption and implementation of “reach” codes stronger than Title 24 on both mandatory and voluntary bases. | 1.1 - Adopt codes, ordinances, standards, guidelines or programs that encourage or require building performance that exceeds state requirements. The focus should be on using existing models, or if there is something new and unique that it be replicable. | 1.1.1. Reach Codes | 1.1.1 – Adopt building energy codes more stringent than Title 24’s requirements, using cost-effectiveness studies by Climate Zone done by the utilities; adopt one or two additional tiers of increasing stringency. | Number of new reach codes
|  | 1.1.2. Green Building Code | 1.1.2 – Adopt a Green Building policy for municipal development, commercial development and/or residential development. | Number of new green building policies
|  | 1.1.3. Point of Sale Program | 1.1.3 – Develop/adopt point of sale programs such as a Residential or Commercial Energy Conservation Ordinance. Focus on whole building performance. | Number of new point of sale programs
|  | 1.1.4. IDSM Code Updates | 1.1.4 – Change local codes to allow and encourage integration of energy efficiency, demand response, and on-site generation. | Number of code updates to encourage IDSM
|  | 1.1.5. Energy Efficiency Codes & Programs | 1.1.5 – Develop and adopt programs to encourage energy efficiency such as one-stop permitting, on-line permitting, separate Zero Net Energy permit processes, density bonuses, or a recognition program. | Number of programs to encourage EE
|  | 1.1.6. Educational Programs | 1.1.6 – Develop educational programs for local elected officials, building officials, commissioners, and stakeholders to improve adoption of energy efficiency codes, ordinances, standards, guidelines and programs. | User-Defined: Use update section to describe goals and progress
| 1.2 - Implement codes, ordinances, standards, guidelines or programs that encourage building performance that exceeds state standards. | 1.2.1. Stakeholder Engagement | 1.2.1 – Implement any of the strategies in section 1.1 through a process involving internal and external stakeholders, etc. | User-Defined: Use update section to describe goals and progress
2 - Strong support from local governments for energy code compliance enforcement. | 2.1 - Improve processes resulting in increased code compliance through education, training, and enforcement practices. | 2.1.1. Code Compliance Workshop Attendance | 2.1.1 – Local government staff and contract staff attend code compliance workshops offered by the California Energy Commission, utility codes & standards staff, or other local governments with strong compliance records. | Number of workshops and attendees.
|  | 2.1.2. Code Compliance and Enforcement | 2.1.2 – Redesign enforcement, compliance, plan review processes; introduce new forms and templates. | User-Defined: Use update section to describe goals and progress
3 - Local governments lead by example with their own facilities and energy usage practices. | 3.1 - Develop a program to track municipal energy usage, such as through energy management software and benchmarking of municipal facilities. | 3.1.1. Local Gov't Benchmarking Policies | 3.1.1 – Develop energy benchmarking policies and procedures to enable ongoing benchmarking of all local government facilities. | Number of new Local Gov't benchmarking policies/procedures.
|  | 3.1.2. Local Gov't 'Utility Manager' Program | 3.1.2 – Set up a ‘utility manager’ computer program to track municipal usage. Identify need for sub-metering to plan, budget and manage bills. | Number of new Local Gov't utility manager programs established
| 3.2 - Adopt an Energy or Climate Action Plan for municipal operations. The plan could include setting energy efficiency standards for new and existing facilities, developing a revolving loan fund for energy efficiency projects, and so on. | 3.2.1. Local Gov't EAP/CAP | 3.2.1 – Develop/adopt an energy chapter for City/ County climate or energy action plan. | Number of new Local Gov't EAPs/CAPs developed
|  | 3.2.2. Local Gov't Building Standard | 3.2.2 – Adopt a policy to require LEED, Energy Star Ratings, or other program standard for municipal facilities. | Number of new Local Gov't LEED/Energy Star/Other policies adopted
|  | 3.2.3. Local Gov't Revolving Energy Efficiency Fund | 3.2.3 – Develop policy for a revolving energy efficiency fund for City/County facilities. | Number of new Local Gov't revolving energy fund policies
|  | 3.2.4. Local Gov't Commissioning/Retro-Commissioning Policy | 3.2.4 – Develop commissioning/retro-commissioning policies for municipal facilities. | Number of new Local Gov't Cx/RCx policies
4 - Local governments lead their communities with innovative programs for energy efficiency, sustainability and climate change. | 4.1 - Adopt a Climate Action Plan (CAP), Energy Action Plan (EAP) or adopt energy efficiency language into another policy document, such as a General Plan, to reduce community greenhouse gas emissions with a focus on energy efficiency. | 4.1.1. Community-Wide EAP/CAP Template | 4.1.1 – Develop a regional template for Climate Action Plans (CAP) or Energy Action Plans (EAP). | Number of EAP/CAP templates
|  | 4.1.2. Customized EAP/CAP | 4.1.2 – Customize CAP with energy efficiency language and data. | Number of EAPs/CAPs customized
|  | 4.1.3. Community-Wide Planning for EE | 4.1.3 – Update General Plan/Conservation Element with Climate policies. Provide energy efficiency framework and data for other people doing planning. | Number of Plans updated
|  | 4.1.4. Community-Wide EE Savings Analysis | 4.1.4 – Conduct the energy efficiency savings analysis for an annual Greenhouse Gas inventory for the City/ County. | Number of EE analyses completed
5 - Local government energy efficiency expertise becomes widespread and typical. |  | 5. EE Expertise | 5 - Local government energy efficiency expertise becomes widespread and typical. | User-Defined: Use update section to describe goals and progress

## SELECTIONS
IOU Partner | Prior Projects | Project Status | Sector | IOU
PG&E | 2013-2015 Continuation | In Progress | Municipal | N/A
SCE | New Project | On-Hold | Residential | PG&E / SCE
SCG | New Phase of Past Project (specify in Description) | Complete | Commercial | PG&E / SCG
SDG&E | Re-Launch of Past Project (specify in Description) | Cancelled | Industrial | PG&E / SCE / SCG
| Update Related to Past Project (specify in Description) |  | Agricultural | SCE / SCG
Other (Please Specify)