## Instructions
Local Government Energy Efficiency Strategic Plan Menu (SPM) - Bi-Annual Reporting
Questions? Contact your IOU Program Manager
IOU Partner:
SCE
Reporting Period:
| Start: | 2017-01-01
| End: | 2017-06-30
Submission Deadline: |  | 2017-09-29
General Instructions
Please complete the "SPM Report" tab for new strategic plan menu (SPM) items from 2016 and continuing SPM items not reported as "Complete" in the 2013-15 cycle.
Please omit any activity completed prior to January 1, 2016.
You will find a complete list of SPM items in the tab labeled "SPM_MenuItems" as reference.
New Projects: | Projects initiated after January 1, 2016.
For each new project, complete all cells within a blank row immediately below the last populated row. Upon review with your Program Manager, the cells highlighted gray will be locked from future editing. This is to facilitate understanding of project scope, and to encourage dialogue regarding changes to scope.
Continuing Projects: | Projects initiated before the current reporting period, which are ongoing.
For continuing projects, changes in initial project scope should be specified. - Revisions to Project Timeline: Changes to the project's timeline should be noted in Column X. - Revisions to Budget: If the budget for a project changes, the new cumulative budget should be reported in Column Y. - Changes to Project Scope: Changes to the project scope (goal, local governments served, etc.) should be noted in Column Z. - Additional details regarding changes in project scope can be detailed in the Narrative Report section.
Completed Projects: | Projects completed after January 1, 2016.
Select "Completed" from the drop-down menu in Column U.
Specify the accomplishments of the project in Column V, and note "Final" in the text. If scoped deliverables are not completed, specify which in Column T.
If a project was completed before or after the planned timeline, specify the completion date in Column X, and note "Final" in the text.
If a project was completed above or below the planned budget, specify the final expenditures in Column Y, and note "Final" in the text.
Cancelled Projects: | Projects which were initiated, but which are deemed to proceed no further.
To the extent possible, document all relevant information in the corresponding cells (e.g. expenditure, accomplishments, etc.).
Provide narrative summary of the actions or inactions that led to the project being cancelled.
If learned lessons can be gleaned from cancelled projects, specify in Column AM (Lessons Learned).
Projects On-Hold: | Projects which are still planned to occur, but which face unanticipated delays.
Provide narrative summary of the actions or inactions that led to the project being placed on-hold. Specify what actions (if known) need to be addressed before the project can resume.
Instructions by Section
Project Scope | Each project line item should be mutually exclusive, and should not include the accomplishments of another.
If project relates to a past project, indicate how it relates using the drop-down in Column E. Specify which past project in the Description in Column F. - New Project: Current project does not directly relate to past project - New Phase of Past Project: Past project as scoped and completed previously; current project builds upon the accomplishments of the past project. - Re-Launch of Past Project: Past project was scoped and either completed, placed on-hold, or cancelled; current project attempts the same/similar effort as past project, but with new project elements to address lessons learned. - Update of Past Project: Past project was scoped and completed previously; current project integrates new information, as in updates to previously adopted code or Climate Action Plan.
Report all project information based on its current, cumulative scope. For instance, provide the full, anticipated cumulative budget based on the scoped goal and timeline.
Select all sectors applicable to the work being performed.
Projects should have a clear beginning and end date.
Projects should have a defined budget. Please report cumulative budget corresponding to the defined timeline.
SPM Alignment | Projects should be scoped to address one primary SMP Item. In some cases, projects may support additional SMP Items; however, if projects are broad enough to cover multiple SMP Items, they should be separately scoped and reported.
Progress Indicators | Specify the deliverables and/or metrics that will mark progress toward completing the goal. For a list of recommended metrics corresponding to SPM goals, refer to the "SPM Menu Items" tab, Column E.
Specify the primary goal of the project. The goal should correspond to the SPM Item the project supports.
If a code-related project, specify whether the goal is to adopt code(s), or to provide other code-support; if the goal is to adopt code(s), specify whether the code(s) are voluntary or mandatory.
To the extent possible, quantify the number of policy documents/plans, anticipated kWh savings and public workshops (as applicable).
Project Status and Accomplish-ments to Date | All projects should have a defined project status (e.g. In Progress, On-Hold, Complete, Cancelled). The project timeline (Start Date / Completion Date) should correspond with project status. If the timeline and status are out of alignment, the cells will highlight red to identify the discrepency.
Accomplishments to-date should refer to deliverables and/or metrics. Report unanticipated or spill-over benefits in the Narrative Report section, and Lessons Learned section (if applicable).
If deliverables or metrics are tied to local governments as recipients (e.g. each city receives a benchmarking report), provide status updates specific to each local government.
Local Government Officials Engaged* | In Columns AA-AE, track the number of government officials or public stakeholers of various types engaged during the reporting period (e.g. January - June).
In Column AF, track the cumulative number of government officials/public stakeholders engaged throughout the duration of the project. This value should draw upon values previously reported.
Narrative Reporting | Provide detailed account of progress made to date, significant acheivements, significant challenges, deliverables or milestones completed, lessons learned, and knowledge transferred. Include anything in this section that could not be clearly articulated in other appropriate cells.
Knowledge Transfer | Document major findings emerging from project implementation under the Lessons Learned section. This should be cumulative, covering the full project duration
If work product is published online, please provide links to the material.

## SPM_Report
Review the grey cells below to ensure the information on your projects remains correct in this reporting period. Scroll to the right to share project updates in all white cells. Contact your IOU Project Manager with any questions.
|  | Project ID |  | Project Scope | [8 empty] | SPM Alignment |  | Progress Indicators |  |  |  |  | Project Status and Accomplishments to Date | [5 empty] | Engagements (This Reporting Period) | [5 empty] | Narrative Reporting | Narrative Reporting | Narrative Reporting | Narrative Reporting | Narrative Reporting | Narrative Reporting | Knowledge Transfer
Due Date |  | Partnership Name | Project Name | Connection to Past Project? | Project Scope and Description (Max 600 Characters) | Applicable Sector | Primary Beneficiary/ies | Multi-IOU Project? | Start Date (MONTH-YYYY) | Original Estimated Completion Date (MONTH-YYYY) | SCE Budget Allocation to Project | Matching Funds Amount and Detail (if applicable) | Primary SPM Item Alignment | Secondary SPM Item Alignment (if applicable) | Specify Deliverable and/or Evaluative Metric | Goal | # Plans or Policies to be Developed (optional) | Estimated Electricity Savings (kWh) (optional) | # of Outreach Events to be Held (optional) | Project Status | Scope Completed to Date | Scope Remaining to be Completed | Revisions to Project Timeline? | Revisions to Project Budget? | Revisions to Project Scope? | Elected / Appointed Officials | Dept Directors / City Manager | Other local gov't staff | Support Staff / Consultant / IOU / Non-Govt | Public / Community Members | Total Engagements | October 2016 Narrative Update (January 1 - June 30, 2016) | March 2017 Narrative Update (July 1 - December 31, 2016) | September 2017 Narrative Update (January 1 - June 30, 2017) | March 2018 Narrative Update (July 1 - December 31, 2017) | September 2018 Narrative Update (January 1 - June 30, 2018) | March 2019 Narrative Update (July 1 - December 31, 2018) | Lessons Learned Reporting (Cumulative) | Links to Work Product or Deliverable?
| 2017-06-30 | San Joaquin Energy Leader Partnership (AKA VIEW Partnership) | Benchmarking in Energy Star Portfolio Manager | New Phase of Past Project (specify in Description) | Embedded 2013-2015: San Joaquin Valley Clean Energy Organization will benchmark of all utility accounts in Energy Star Portfolio Manager (ESPM) for VIEW partners. Also includes training of local government staff on use of Portfolio Manager. | Public | Cities of Porterville, Tulare and Woodlake and Counties of Kings and Tulare | PG&E / SCE / SCG | 2015-01-01 | 2016-12-01 | $13,500 (PG&E) / $13,500 (SCE) / $1,400 (SCG) | 0 | 3.1.1. Local Gov't Benchmarking Policies | N/A | Benchmarked portfolios for the County of Tulare. All utility accounts will be benchmarked in ESPM, County will use a benchmarking policy to impact procurement and investment decisions, and staff will be trained on program use. | Municipal staff in all local governments enrolled in Portfolio Manager and automated benchmarking services and actively engaged in data analysis. | 5 | 16441200 | 0 | In Progress | 1. Completed benchmarking for: County of Kings, Cities of Avenal, Dinuba, Hanford, Woodlake | 1. Complete SCG benchmarking for Tulare County and Cities of Porterville and Tulare. Begin benchmarking processes for Corcoran and Lemoore | Project to continue in 2017 for Tulare County. Project has not been started for Corcoran or Lemoore. | None | None | 1 | 0 | 4 | 2 | 0 | 7 | 1. City and county energy accounts have been scrubbed for accuracy and duplicates/dead accounts have been removed from the portfolio 2. Met with city/county staff to review facility characteristics 3. Worked with IOU representatives to collect accurate energy data and set up Automatic Benchmarking for the cities and counties. 4. Benchmarking is now complete for the County of Kings as well as the Cities of Avenal, Dinuba, Farmersville, Hanford, Lindsay, Visalia, and Woodlake. | 1. No changes. Continue to perform maintenance as necessary. 2. Working with County of Tulare to get accurate building data characteristics for one-time data upload into ESPM. | 1. ESPM glitches include a) duplicated SCE data, requiring account review and maintenance when data reports are needed and b) no SCG energy usage cost uploads, prohibiting local government staff and implementer staff to fully report on and analyze usage data. 2. Local governments that lack comprehensive facility inventories add significant workload to the benchmarking process. |  |  |  | 1. ESPM glitches include a) duplicated SCE and PG&E data, requiring ongoing account review and maintenance when data reports are needed and b) no SCG energy usage cost uploads, prohibiting local government staff and implementer staff to fully report on and analyze usage data. 2. Local governments that lack comprehensive facility inventories add significant workload to the benchmarking process. 3. New requirements for AB 802 compliance will increase the workload for the benchmarking process significantly. Creating accounts in each utility's individual dashboard will double the process for account uploads as will obtaining authorization requirements.
| 2017-06-30 | San Joaquin Energy Leader Partnership (AKA VIEW Partnership) | Energy Action Plans | New Phase of Past Project (specify in Description) | Embedded 2013-2015: San Joaquin Valley Clean Energy Organization will create customized Energy Action Plans or Climate Action Plans to fit the needs of individual cities while maintaining a regional focus. | Public Residential Commercial Industrial Agricultural | City of Hanford and County of Kings | PG&E / SCE / SCG | 2015-01-01 | 2016-12-01 | $13,500 (PG&E) / $13,500 (SCE) / $1,400 (SCG) | 0 | 4.1.2. Customized EAP/CAP | N/A | Council ready EAP. The EAP may or may not be approved by council (concerns regarding document as a planning document exist and are being reviewed by local government counsel). If document is not formally adopted the LG will institute department strategies and use the document as a guiding principle document to influence staff activities. | Adoption, either at council or internally, of a customized energy action plan. | 2 | 0 | 0 | In Progress | 1. Kings County EAP complete and approved 2. City of Hanford EAP complete; on hold until Spring 2017 | 1. Begin EAP process for all other VIEW jurisdictions. | Project to continue into 2017 as EAPs for other VIEW jurisdictions are started. | None | None | 0 | 1 | 5 | 3 | 0 | 9 | 1. The County of Kings has completed the development of its EAP and, once the County completes document review, will bring the document to Council for approval 2. The City of Hanford has adopted a CAP independent of the Partnership. The City has completed approximately 70% of its EAP. | 1. The County board and SCE approved the Energy Action Plan for the County of Kings. This allowed the County to move to Gold on the SCE tier ladder and begin preparations for implementation of the Plan. 2. The EAP for the City of Hanford was completed and presented to the City. Due to an upcoming update to the City's General Plan and the election of new Council members, the City has put a hold on moving forward with the EAP until Spring 2017. | Each local government requires different language and layouts of EAPs, which can sometimes significantly increase the workload of this project. |  |  |  | Each local government requires different language and layouts of EAPs, which can sometimes significantly increase the workload of this project. New requirements for AB 802 compliance may stymie the Needs Evaluation and Assessment of Data process due to more time-consuming requests.
| 2017-06-30 | Gateway Cities/Long Beach | Energy Action Plans/Benchmarking | New Project | Preliminary Energy Analyses & Benchmarking to establish building energy-usage intensities (EUIs). Facility Audits & Measure Identification will be conducted for a thorough review of all equipment in the facilities and recommendations given for energy efficiency measures, including lighting systems, HVAC systems, and building envelope systems. Integration of results into the Energy Action Plan that prioritizes each City’s investments to reach the City’s short- and long-term goals incorporating lessons learned and observations that will benefit each City’s capital renewal, maintenance and operations. | Public | Long Beach, Lynwood, Lakewood | SCE / SCG | 2017-02-01 | 2017-06-01 | 80000 |  | 3.1.1. Local Gov't Benchmarking Policies |  | Benchmarked portfolios & Council approved EAPs for the Cities of Lakewood, Long Beach & Lynwood. | Enrollment in Portfolio Manager for active data analysis along with automated benchmarking services. Adoption of customized energy action plan for each city. | 3 |  |  | In Progress | Completed benchmarking for Lakewood. | Benchmarking for Long Beach & Lynwood. EAPs for Lakewood, Long Beach & Lynwood | Project to continue to end of 2017 | None | None | [5 empty] | 0 | N/A | N/A | Competed the draft benchmarking reports for the City of Lakewood and Lynwood. Both have been approved and finalized at this time. A draft Energy Action Plan has been submitted for Lakewood, and is currently undergoing further revisions. The draft EAP for Lynwood is in progress. Scoping audits were conducted for both Lakewood and Lynwood. The City of Long Beach is currently in the initial benchmarking stage.
| 2017-06-30 | San Gabriel Valley | Benchmarking | New Project | Develop a policy and procedure to implement benchmarking for participating cities. Establish a baseline for performance for all eligible City facilities. Develop a streamlined process for energy performance data management and identify opportunities and strategies for improving energy performance in city facilities moving forward. Enable verification that City is making progress toward local and State requirements around improving energy performance and reducing greenhouse gas emissions. | Public | Monrovia, Pomona, South Pasadena, West Covina | SCE / SCG | 2017-01-01 | 2017-12-01 | 80000 |  | 3.1.1. Local Gov't Benchmarking Policies |  | Benchmarking policy approved by cities of Monrovia, Pomona, South Pasadena, West Covina. | Adoption, either at council or internally, of a customized benchmarking policy. | 4 |  |  | In Progress | Completed Benchmarking Policy assessment & planning report | Draft benchmarking policies for each city along with final program report. | None | None | None | [5 empty] | 0 | N/A | •Applied for Strategic Plan grant funding through SCE. •Hosted Benchmarking Workshop for SGVEWP City staffers. •Drafted a budget of about $80,000 for the SCE Strategic Plan Benchmarking Project. •Identified benchmarking software tool to be utilized for municipal facilities' benchmarking: EPA's Energy Star Portfolio Manager. •Began drafting SGVEWP municipal building database | •Drafted a thorough municipal database of all facilities of participating cities and additional potential participating cities in the SGVEWP. •Drafted and completed Assessment and Planning Report. •Drafted and completed the SGV Energy Benchmarking Policy (includes: Benchmarking Purpose and Goals, Benchmarking Policy Procedures, & Benchmarking Policy Implementation provisions). •Conducted initial and follow-up benchmarking policy meetings with environmental services and/or public works analysts, directors, and implementers of each of the four Cities. •Set up separate Portfolio Manager accounts for each of the 4 participating Cities. •Completed mutli-step process of enrolling in SCG's Web Services for "Automated Benchmarking" on Portfolio Manager. •Plethora of applicable gas usage data for Cities' facilities have been uploaded to proper Portfolio Manager accounts and meters. •As part of SCE's data sharing services process, completed property ownership verification process, and thus obtained 'Data Sharing Keys' for majority of Cities' facilities. •To date, 3 municipalities have formally adopted the Policy as an internal policy.
| 2017-06-30 | Ventura County | Benchmarking | New Project | Benchmark facilities that are over 10,000 square feet for the jurisdictions of Camarillo, Fillmore, Moorpark, Ojai, Oxnard, Port Hueneme, Santa Paula, Simi Valley, Thousand Oaks, Ventura and Ventura County. | Public | Camarillo, Fillmore, Moorpark, Ojai, Oxnard, Port Hueneme, Santa Paula, Simi Valley, Thousand Oaks, and Ventura and the County of Ventura | SCE / SCG | 2017-05-01 | 2018-04-01 | 48510 |  | 3.1.1. Local Gov't Benchmarking Policies |  | Benchmarked portfolios for Camarillo, Fillmore, Moorpark, Ojai, Oxnard, Port Hueneme, Santa Paula, Simi Valley, Thousand Oaks, Ventura and Ventura County. All utility accounts over 10,000 sqft. will be benchmarked in ESPM. | Enrollment in Portfolio Manager and automated benchmarking services and actively engaged in data analysis by municipal staff. | 11 |  |  | In Progress | Preliminary draft of assessment & planning report being prepared. | Completion of enrollment of city/county facilities in ESPM. | None | None | None | [5 empty] | 0 | N/A | N/A | Letters of support has been submitted for all partners. CISR forms have been submitted numerous times to SCE for data required to enroll facilities in benchmarking. VCREA has also provided suggestions on requirements on Title for benchmarking enrollment of facilities in Portfolio Manager. Work has not formally begun due to the delays in data processes
| 2017-06-30 | High Desert | Benchmarking | New Project | Benchmark of all utility accounts in Energy Star Portfolio Manager (ESPM) along with training of local government staff on use of Portfolio Manager. | Public | Barstow, Hesperia, and Victorville | SCE / SCG | 2017-03-14 | 2018-02-01 | 22500 |  | 3.1.1. Local Gov't Benchmarking Policies |  | Benchmarked portfolios for Barstow, Hesperia, and Victorville. All utility accounts will be benchmarked in ESPM. | Enrollment in Portfolio Manager and automated benchmarking services and actively engaged in data analysis by municipal staff. | 3 |  |  | On-Hold | Awaiting city support letters. | Completion of enrollment of city/county facilities in ESPM. | None | None | None | [5 empty] | 0 | N/A | N/A | All letters of support have been submitted. Work is pending updates to SCE's PO's and has been slowed due to SCE requirements on titles to enroll facilities in ES Portfolio Manager
|  | High Desert | Energy Action Plans | New Project | Creation of customized Energy Action Plan to fit the needs of Hesperia. | Public | Hesperia | SCE / SCG | 2017-03-14 | 2018-02-01 | 5600 |  | 3.2.1. Local Gov't EAP/CAP |  | Council approved Municipal EAP | Adoption, either at council or internally, of a customized energy action plan. | 1 |  |  | On-Hold | Preliminary draft of assessment & planning report. | EAP and final program report. | None | None | None | [6 empty] | N/A | N/A | Work is pending change order to SCE's PO to allow for work to be billed.
| 2017-06-30 | San Joaquin Energy Leader Partnership (AKA VIEW Partnership) | Energy Action Plans | New Project | Creation of customized Energy Action Plans to fit the needs of Hanford, Lindsay, Woodlake, & Tulare County. | Public | Hanford, Lindsay, Woodlake, and the County of Tulare | PG&E / SCE / SCG | 2017-01-01 | 2017-12-01 | 28400 |  | 3.2.1. Local Gov't EAP/CAP |  | Council approved EAPs for Hanford, Lindsay, Woodlake, & Tulare County. | Adoption, either at council or internally, of a customized energy action plan. | 4 |  |  | On-Hold | Preliminary draft of assessment & planning report. | EAP and final program report. | None | None | None | [5 empty] | 0 | N/A | N/A | Each local government requires different language and layouts of EAPs, which can sometimes significantly increase the workload of this project.
| 2017-06-30 | San Joaquin Energy Leader Partnership (AKA VIEW Partnership) | Benchmarking | New Project | Benchmark of all utility accounts in Energy Star Portfolio Manager (ESPM) along with training of local government staff on use of Portfolio Manager. | Public | County of Tulare | PG&E / SCE / SCG | 2017-01-01 | 2017-12-01 | 8500 |  | 3.1.1. Local Gov't Benchmarking Policies |  | Benchmarked portfolios for Tulare County. All utility accounts will be benchmarked in ESPM. | Enrollment in Portfolio Manager and automated benchmarking services and actively engaged in data analysis by municipal staff. | 1 |  |  | On-Hold | Awaiting city support letters. | Completion of enrollment of county facilities in ESPM. | None | None | None | [5 empty] | 0 | N/A | N/A | 1. Awaiting CEC approval on AB802 revision to Draft regulations. The revision will remove the requirement to provide a deed of ownership for facilities to entered into ESPM. 2. ESPM glitches are prohibiting local government staff and implementer staff to fully report on and analyze utility usage data. 3. Local governments that lack comprehensive facility inventories add significant workload to the benchmarking process.
| 2017-06-30 | [29 empty] | 0
| 2017-06-30 | [29 empty] | 0
| 2017-06-30 | [29 empty] | 0
| 2017-06-30 | [29 empty] | 0
| 2017-06-30 | [29 empty] | 0
| 2017-06-30 | [29 empty] | 0
| 2017-06-30 | [29 empty] | 0
| 2017-06-30 | [29 empty] | 0
| 2017-06-30 | [29 empty] | 0
| 2017-06-30 | [29 empty] | 0
| 2017-06-30 | [29 empty] | 0
| 2017-06-30 | [29 empty] | 0
| 2017-06-30 | [29 empty] | 0
| 2017-06-30 | [29 empty] | 0
| 2017-06-30 | [29 empty] | 0
| 2017-06-30 | [29 empty] | 0
| 2017-06-30 | [29 empty] | 0
| 2017-06-30 | [29 empty] | 0
| 2017-06-30 | [29 empty] | 0
| 2017-06-30 | [29 empty] | 0
| 2017-06-30 | [29 empty] | 0
| 2017-06-30 | [29 empty] | 0
| 2017-06-30 | [29 empty] | 0
| 2017-06-30 | [29 empty] | 0
| 2017-06-30 | [29 empty] | 0
| 2017-06-30 | [29 empty] | 0
| 2017-06-30 | [29 empty] | 0
| 2017-06-30 | [29 empty] | 0
| 2017-06-30 | [29 empty] | 0
| 2017-06-30 | [29 empty] | 0
| 2017-06-30 | [29 empty] | 0
| 2017-06-30 | [29 empty] | 0
| 2017-06-30 | [29 empty] | 0
| 2017-06-30 | [29 empty] | 0
| 2017-06-30 | [29 empty] | 0
| 2017-06-30 | [29 empty] | 0
| 2017-06-30 | [29 empty] | 0
| 2017-06-30 | [29 empty] | 0
| 2017-06-30 | [29 empty] | 0
| 2017-06-30 | [29 empty] | 0
| 2017-06-30 | [29 empty] | 0
| 2017-06-30 | [29 empty] | 0
| 2017-06-30 | [29 empty] | 0
| 2017-06-30 | [29 empty] | 0
| 2017-06-30 | [29 empty] | 0
| 2017-06-30 | [29 empty] | 0
| 2017-06-30 | [29 empty] | 0
| 2017-06-30 | [29 empty] | 0
| 2017-06-30 | [29 empty] | 0
| 2017-06-30 | [29 empty] | 0
| 2017-06-30 | [29 empty] | 0
| 2017-06-30 | [29 empty] | 0
| 2017-06-30 | [29 empty] | 0
| 2017-06-30 | [29 empty] | 0
| 2017-06-30 | [29 empty] | 0
| 2017-06-30 | [29 empty] | 0
| 2017-06-30 | [29 empty] | 0
| 2017-06-30 | [29 empty] | 0
| 2017-06-30 | [29 empty] | 0
| 2017-06-30 | [29 empty] | 0
| 2017-06-30 | [29 empty] | 0
| 2017-06-30 | [29 empty] | 0
| 2017-06-30 | [29 empty] | 0
| 2017-06-30 | [29 empty] | 0
| 2017-06-30 | [29 empty] | 0
| 2017-06-30 | [29 empty] | 0
| 2017-06-30 | [29 empty] | 0
| 2017-06-30 | [29 empty] | 0
| 2017-06-30 | [29 empty] | 0
| 2017-06-30 | [29 empty] | 0
| 2017-06-30 | [29 empty] | 0
| 2017-06-30 | [29 empty] | 0
| 2017-06-30 | [29 empty] | 0
| 2017-06-30 | [29 empty] | 0
| 2017-06-30 | [29 empty] | 0
| 2017-06-30 | [29 empty] | 0
| 2017-06-30 | [29 empty] | 0
| 2017-06-30 | [29 empty] | 0
| 2017-06-30 | [29 empty] | 0
| 2017-06-30 | [29 empty] | 0
| 2017-06-30 | [29 empty] | 0
| 2017-06-30 | [29 empty] | 0
| 2017-06-30 | [29 empty] | 0
| 2017-06-30 | [29 empty] | 0
| 2017-06-30 | [29 empty] | 0
| 2017-06-30 | [29 empty] | 0
| 2017-06-30 | [29 empty] | 0
| 2017-06-30 | [29 empty] | 0
| 2017-06-30 | [29 empty] | 0
| 2017-06-30 | [29 empty] | 0
| 2017-06-30 | [29 empty] | 0
| 2017-06-30 | [29 empty] | 0
| 2017-06-30 | [29 empty] | 0
| 2017-06-30 | [29 empty] | 0
| 2017-06-30 | [29 empty] | 0
| 2017-06-30 | [29 empty] | 0
| 2017-06-30 | [29 empty] | 0
| 2017-06-30 | [29 empty] | 0
| 2017-06-30 | [29 empty] | 0
| 2017-06-30 | [29 empty] | 0
| 2017-06-30 | [29 empty] | 0
| 2017-06-30 | [29 empty] | 0
| 2017-06-30 | [29 empty] | 0
| 2017-06-30 | [29 empty] | 0
| 2017-06-30 | [29 empty] | 0
| 2017-06-30 | [29 empty] | 0
| 2017-06-30 | [29 empty] | 0
| 2017-06-30 | [29 empty] | 0
| 2017-06-30 | [29 empty] | 0
| 2017-06-30 | [29 empty] | 0
| 2017-06-30 | [29 empty] | 0
| 2017-06-30 | [29 empty] | 0
| 2017-06-30 | [29 empty] | 0
| 2017-06-30 | [29 empty] | 0
| 2017-06-30 | [29 empty] | 0
| 2017-06-30 | [29 empty] | 0
| 2017-06-30 | [29 empty] | 0
| 2017-06-30 | [29 empty] | 0
| 2017-06-30 | [29 empty] | 0
| 2017-06-30 | [29 empty] | 0
| 2017-06-30 | [29 empty] | 0
| 2017-06-30 | [29 empty] | 0
| 2017-06-30 | [29 empty] | 0
| 2017-06-30 | [29 empty] | 0
| 2017-06-30 | [29 empty] | 0
| 2017-06-30 | [29 empty] | 0
| 2017-06-30 | [29 empty] | 0
| 2017-06-30 | [29 empty] | 0
| 2017-06-30 | [29 empty] | 0
| 2017-06-30 | [29 empty] | 0
| 2017-06-30 | [29 empty] | 0
| 2017-06-30 | [29 empty] | 0
| 2017-06-30 | [29 empty] | 0
| 2017-06-30 | [29 empty] | 0
| 2017-06-30 | [29 empty] | 0
x | x | x | xx | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | [5 empty] | x | x

## SPM_MenuItems
Goal | Strategy | Menu Option - Abbreviated Title | Menu Option- Full Text | Metric
1 - Local governments lead adoption and implementation of “reach” codes stronger than Title 24 on both mandatory and voluntary bases. | 1.1 - Adopt codes, ordinances, standards, guidelines or programs that encourage or require building performance that exceeds state requirements. The focus should be on using existing models, or if there is something new and unique that it be replicable. | 1.1.1. Reach Codes | 1.1.1 – Adopt building energy codes more stringent than Title 24’s requirements, using cost-effectiveness studies by Climate Zone done by the utilities; adopt one or two additional tiers of increasing stringency. | Number of new reach codes
|  | 1.1.2. Green Building Code | 1.1.2 – Adopt a Green Building policy for municipal development, commercial development and/or residential development. | Number of new green building policies
|  | 1.1.3. Point of Sale Program | 1.1.3 – Develop/adopt point of sale programs such as a Residential or Commercial Energy Conservation Ordinance. Focus on whole building performance. | Number of new point of sale programs
|  | 1.1.4. IDSM Code Updates | 1.1.4 – Change local codes to allow and encourage integration of energy efficiency, demand response, and on-site generation. | Number of code updates to encourage IDSM
|  | 1.1.5. Energy Efficiency Codes & Programs | 1.1.5 – Develop and adopt programs to encourage energy efficiency such as one-stop permitting, on-line permitting, separate Zero Net Energy permit processes, density bonuses, or a recognition program. | Number of programs to encourage EE
|  | 1.1.6. Educational Programs | 1.1.6 – Develop educational programs for local elected officials, building officials, commissioners, and stakeholders to improve adoption of energy efficiency codes, ordinances, standards, guidelines and programs. | User-Defined: Use update section to describe goals and progress
| 1.2 - Implement codes, ordinances, standards, guidelines or programs that encourage building performance that exceeds state standards. | 1.2.1. Stakeholder Engagement | 1.2.1 – Implement any of the strategies in section 1.1 through a process involving internal and external stakeholders, etc. | User-Defined: Use update section to describe goals and progress
2 - Strong support from local governments for energy code compliance enforcement. | 2.1 - Improve processes resulting in increased code compliance through education, training, and enforcement practices. | 2.1.1. Code Compliance Workshop Attendance | 2.1.1 – Local government staff and contract staff attend code compliance workshops offered by the California Energy Commission, utility codes & standards staff, or other local governments with strong compliance records. | Number of workshops and attendees.
|  | 2.1.2. Code Compliance and Enforcement | 2.1.2 – Redesign enforcement, compliance, plan review processes; introduce new forms and templates. | User-Defined: Use update section to describe goals and progress
3 - Local governments lead by example with their own facilities and energy usage practices. | 3.1 - Develop a program to track municipal energy usage, such as through energy management software and benchmarking of municipal facilities. | 3.1.1. Local Gov't Benchmarking Policies | 3.1.1 – Develop energy benchmarking policies and procedures to enable ongoing benchmarking of all local government facilities. | Number of new Local Gov't benchmarking policies/procedures.
|  | 3.1.2. Local Gov't 'Utility Manager' Program | 3.1.2 – Set up a ‘utility manager’ computer program to track municipal usage. Identify need for sub-metering to plan, budget and manage bills. | Number of new Local Gov't utility manager programs established
| 3.2 - Adopt an Energy or Climate Action Plan for municipal operations. The plan could include setting energy efficiency standards for new and existing facilities, developing a revolving loan fund for energy efficiency projects, and so on. | 3.2.1. Local Gov't EAP/CAP | 3.2.1 – Develop/adopt an energy chapter for City/ County climate or energy action plan. | Number of new Local Gov't EAPs/CAPs developed
|  | 3.2.2. Local Gov't Building Standard | 3.2.2 – Adopt a policy to require LEED, Energy Star Ratings, or other program standard for municipal facilities. | Number of new Local Gov't LEED/Energy Star/Other policies adopted
|  | 3.2.3. Local Gov't Revolving Energy Efficiency Fund | 3.2.3 – Develop policy for a revolving energy efficiency fund for City/County facilities. | Number of new Local Gov't revolving energy fund policies
|  | 3.2.4. Local Gov't Commissioning/Retro-Commissioning Policy | 3.2.4 – Develop commissioning/retro-commissioning policies for municipal facilities. | Number of new Local Gov't Cx/RCx policies
4 - Local governments lead their communities with innovative programs for energy efficiency, sustainability and climate change. | 4.1 - Adopt a Climate Action Plan (CAP), Energy Action Plan (EAP) or adopt energy efficiency language into another policy document, such as a General Plan, to reduce community greenhouse gas emissions with a focus on energy efficiency. | 4.1.1. Community-Wide EAP/CAP Template | 4.1.1 – Develop a regional template for Climate Action Plans (CAP) or Energy Action Plans (EAP). | Number of EAP/CAP templates
|  | 4.1.2. Customized EAP/CAP | 4.1.2 – Customize CAP with energy efficiency language and data. | Number of EAPs/CAPs customized
|  | 4.1.3. Community-Wide Planning for EE | 4.1.3 – Update General Plan/Conservation Element with Climate policies. Provide energy efficiency framework and data for other people doing planning. | Number of Plans updated
|  | 4.1.4. Community-Wide EE Savings Analysis | 4.1.4 – Conduct the energy efficiency savings analysis for an annual Greenhouse Gas inventory for the City/ County. | Number of EE analyses completed
5 - Local government energy efficiency expertise becomes widespread and typical. |  | 5. EE Expertise | 5 - Local government energy efficiency expertise becomes widespread and typical. | User-Defined: Use update section to describe goals and progress

## SELECTIONS
IOU Partner | Prior Projects | Project Status | Sector | IOU
PG&E | 2013-2015 Continuation | In Progress | Municipal | N/A
SCE | New Project | On-Hold | Residential | PG&E / SCE
SCG | New Phase of Past Project (specify in Description) | Complete | Commercial | PG&E / SCG
SDG&E | Re-Launch of Past Project (specify in Description) | Cancelled | Industrial | PG&E / SCE / SCG
| Update Related to Past Project (specify in Description) |  | Agricultural | SCE / SCG
Other (Please Specify)